## Common
Common to all ALICE systems
Maintenance Tracking
Task | Type | Location | Duration | Resp. | Status | Date | Comment
Longtime logging with Oracle DB | Consolidation |  |  | SH
Migration to PVSS | Consolidation |  |  | SH
WEB pages for shifters | Consolidation |  |  | SH
Install sensors in experiment modules (temperature and pressure) | Consolidation | SGX2+CR5 | 40h | PC
Relocate few flammable gas detection heads in SGX2 | Consolidation | SGX2 |  | TS (D.Hay)
Analysis Devices Verification/Calibration | Maintenance | SGX2 |  | LP
Flexible to analyses bottles | Consolidation | SGX2 | 2h | AW
Done
Not Done
Note on D10: carrie: il manque les cables entre le CR5 et UX ??

## TPC
ALICE TPC
Maintenance Tracking
Task | Type | Location | Duration | Resp. | Status | Date | Comments
Check electrovalves in purifiers | Maintenance | SGX2 | 1h | VD
Check of pumps | Maintenance | CR5 | 1d | AW PC
Control Mass Flow Controllers (ONLY LOW FLOW) | Maintenance | SGX2 | 3d | VD
Cleaning of mechanical filters | Maintenance | SGX2+UXC | 3d | AW
Safety Valves | Maintenance | SGX2+UXC | 4d | AW
Bubblers (check and oil level) | Maintenance | UX | 2d | AW
Check valves regulation Von-Rohr | Maintenance | CR5 | 2 h | PC
Control of connections electric (400VAC-24VDC) | Maintenance | SGX2 + CR5 | 8 h | PC
Manometers (Tescom and Blondell) | Repair | CR5 |  | AW
Control signal 4-20ma of flow on the Krohne of the puifiers | Repair | SGX2 | 1h | PC
Controls _ Purifier stoppage | Repair |  |  | SH
Backup repair (To be done when system ON) | Consolidation | CR5 | 2d | FM
Install lock on main supply blue valves | Consolidation | UX | 1d | AW
Rears and front dors | Consolidation | SGX2 | 1h | AW
Control and status module PLC | Consolidation | SGX2 | 3d | PC
Status module PLC | Consolidation | CR5 | 3d | PC
Upgrade saferty system in high P buffers | Consolidation |  | 1d | AW
Tighness tests | Test | CR5 | 4d | AW + FM

## TRD
ALICE TRD
Maintenance Tracking
Task | Type | Location | Duration | Resp. | Status | Date | Comments
Check electrovalves in purifiers | Maintenance | SGX2 | 1h | VD
Check of pumps | Maintenance | CR5 | 1d | AW
Control Mass Flow Controllers (LOW FLOW ONLY) | Maintenance | SGX2 | 3d | VD
Cleaning of mechanical filters | Maintenance | SGX2+UXC | 3d | AW
Safety Valves | Maintenance | SGX2+UXC | 4d | AW
Bubblers (check and oil level) | Maintenance | UX | 2d | AW
Check valves regulation Von-Rohr | Maintenance | CR5 | 2 h | PC
Control of connections electric (400VAC-24VDC) | Maintenance | SGX2 + CR5 | 8 h | PC
Remote power cycle Control Chassis (CR5) Reset ELMB | Repair | CR5 | 2h | PC
Wiring Control Chassis (SG, CR5) LED red | Repair | SGX2, CR5 | 2h | PC
Modification of the wiring of the flowcells | Repair | CR5 | 2h | PC
Control signal 4-20ma of flow on the Krohne of the puifiers | Repair | SGX2 | 1h | PC AW
Manometers (Tescom and Blondell) | Repair | CR5 |  | AW
Controls - Purifier stoppage | Repair |  |  | SH
Controls - Swapped PT and DPT | Repair |  |  | SH
Analysis "Goffy" Tighness Comissioning | Consolidation | CR5 | 3d | AW
Membrane gas rack Rotarex outlet valve | Consolidation | SGX2 | 4h | AW
Exhaust module valve to back-pressure reg. | Consolidation | SGX2 | 2h | AW
Tighness tests | Test | CR5 | 4d | AW + FM

## TOF
ALICE TOF
Maintenance Tracking
Task | Type | Location | Duration | Resp. | Status | Date | Comments
Change purifier agents | Maintenance | SGX2 | 3d | VD
Check electrovalves in purifiers | Maintenance | SGX2 | 1h | VD
Check of pumps | Maintenance | CR5 | 1d | AW
Control Mass Flow Controllers | Maintenance | SGX2 | 3d | VD
Cleaning of mechanical filters | Maintenance | SGX2+UXC | 3d | AW
Safety Valves | Maintenance | SGX2+UXC | 4d | AW
Bubblers (check and oil level) | Maintenance | UX | 2d | AW
Check valves regulation Von-Rohr | Maintenance | CR5 | 2 h | PC
Control of connections electric (400VAC-24VDC) | Maintenance | SGX2 + CR5 | 8 h | PC
Remote power cycle Control Chassis (CR5) Reset ELMB | Repair | CR5 | 2h | PC
Wiring Control Chassis (SG, CR5) LED red | Repair | SGX2, CR5 | 2h | PC
Checking of power supplies 24Vdc | Repair | CR5 | 2h | PC SP
Control signal 4-20ma of flow on the Krohne of the puifiers | Repair | SGX2 | 1h | PC
Manometers (Tescom and Blondell) | Repair | CR5 |  | AW
Leak rack 62 | Repair | UX | 1d | AW
Tescom PCV SF6 bad regulation "dust" | Repair | SGX2 | 2h | AW
Check tightness of purge line near Kr source | Repair | SGX2 | 2h | AW
Modification Exhaust Rack (Zimmerli) | Consolidation | SGX2 | 2d | FM
Put in place and connection PT-6204 | Consolidation | UX | 1d | AW
Panel CO2/C2H2F4 non return valves | Consolidation | CR5 | 1d | AW
Tighness tests | Test | CR5 | 4d | AW + FM

## HMPID
ALICE HMPID
Maintenance Tracking
Task | Type | Location | Duration | Resp. | Status | Date | Comment
Control Mass Flow Controllers | Maintenance | SGX2 | 2d | VD
Safety Valves | Maintenance | SGX2+CR5 | 4d | AW
Bubblers (check and oil level) | Maintenance | CR5 | 1d | AW
Verification analysis devices | Maintenance | CR5 | 1d | LP
Purifier cartridge | Maintenance | CR5 | 1d | AW
Control of connections electric (400VAC-24VDC) | Maintenance | SGX2 + CR5 | 8 h | PC
Remote power cycle Control Chassis (CR5) ELMB | Repair | CR5 |  | PC
Wiring Control Chassis (SG, CR5) LED red | Repair | SGX2, CR5 |  | PC
Non return valves CH4/Ar | Consolidation | SGX2 | 2h | AW
Tighness tests | Test | CR5 | 4d | AW + FM
Done
Not Done

## TRIGGER
ALICE Muon-TRIGGER
Maintenance Tracking
Task | Type | Location | Duration | Resp. | Status | Date | Comment
Control Mass Flow Controllers | Maintenance | SGX2 | 3d | VD
Safety Valves | Maintenance | SGX2 | 4d | AW
Bubblers (check and oil level) | Maintenance | UX | 1d | AW
Control of connections electric (400VAC-24VDC) | Maintenance | SGX2 + CR5 | 8 h | PC
Remote power cycle Control Chassis (CR5) Reset ELMB | Repair | CR5 | 2h | PC
Wiring Control Chassis (SG, US) Led red | Repair | SGX5, CR5 | 2h | PC
Manometers (Tescom and Blondell) | Repair | CR5 |  | AW
Tescom PCV iC4H10 bad regulation "dust" | Repair | SGX2 | 2h | AW
Non return valves iC4H10, neutral gas | Consolidation | SGX2 | 2h | AW
Tighness tests | Test | CR5 | 4d | AW + FM
Done
Not Done

## PMD
ALICE PMD
Maintenance Tracking
Task | Type | Location | Duration | Resp. | Status | Date | Comments
Control Mass Flow Controllers | Maintenance | SGX2 | 3d | VD
Safety Valves | Maintenance | SGX2 | 4d | AW
Bubblers (check and oil level) | Maintenance | UX | 1d | AW
Control of connections electric (400VAC-24VDC) | Maintenance | SGX2 + CR5 | 8 h | PC
Remote power cycle Control Chassis (CR5) reset elmb | Repair | CR5 | 2h | PC
Wiring Control Chassis (SG, CR5) led red | Repair | SGX2, CR5 | 2h | PC
Manometers (Tescom and Blondell) | Repair | CR5 |  | AW
Tighness tests | Test | CR5 | 4d | AW + FM
Done
Not Done

## CPV
ALICE CPV
Maintenance Tracking
Task | Type | Location | Duration | Resp. | Status | Date | Comments
Control Mass Flow Controllers | Maintenance | SGX2 | 3d | VD
Safety Valves | Maintenance | SGX2 | 4d | AW
Bubblers (check and oil level) | Maintenance | UX | 1d | AW
Control of connections electric (400VAC-24VDC) | Maintenance | SGX2 + CR5 | 8 h | PC
Remote power cycle Control Chassis (CR5) reset elmb | Repair | CR5 | 2h | PC
Wiring Control Chassis (SG, CR5) led red | Repair | SGX2, CR5 | 2h | PC
Manometers (Tescom and Blondell) | Repair |  |  | AW
Tighness tests | Test | CR5 | 4d | AW + FM
Done
Not Done

## TRACKING
ALICE TRACKING
Maintenance Tracking
Task | Type | Location | Duration | Resp. | Status | Date | Comments
Control Mass Flow Controllers | Maintenance | SGX2 | 3d | VD
Safety Valves | Maintenance | SGX2 | 4d | AW
Bubblers (check and oil level) | Maintenance | UX | 1d | AW
Control of connections electric (400VAC-24VDC) | Maintenance | SGX2 + CR5 | 8 h | PC
Remote power cycle Control Chassis (CR5) reset elmb | Repair | CR5C | 2h | PC
Wiring Control Chassis (SG, CR5) led red | Repair | SGX5, CR5 | 2h | PC
Manometers (Tescom and Blondell) | Repair | CR5 |  | AW
Tighness tests | Test | CR5 | 4d | AW + FM
Done
Not Done