## two sectors
|  | Duration | Intensity | # shots | ò Intensity | Comments | Names | EIC | Operator | HWC -EIC | HWC -OP
|  | h | p+ |  | p+
Friday 14:00 | Close LHC
approx 18:00 | S23 Injection region setup & beam to 3 | 2 | 5000000000 | 360 | 1800000000000 | Same settings at last time - should be straightforward | OP
22:00 - 24:00 | BLM threshold test 23 | 2 | 5000000000 | 360 | 1800000000000 |  | Bernd
SAT 00:00 - 04:00 | Polarity checks 23 - revisited | 4 | 5000000000 | 720 | 3600000000000 |  | Frank Zimmermann & co
04:00 - 06:00 | Beam losses and transmission studies with different collimator settings in IP3 | 2 | 5000000000 | 360 | 1800000000000 |  | Stefano & co | Mirko - N | Ron - N
06:00 - 08:00 | Momentum aperture measurements in sector 2-3 (arc + IP) | 2 | 5000000000 | 360 | 1800000000000 |  | Stefano & co | 4
08:00 - 10:00 | TI2/8 momentum aperture / LHC fRF trim range checks | 2 | 5000000000 | 360 | 1800000000000 |  | Jorg
10:00 - 13:00 | Alice Spectrometer | 3 | 5000000000 | 540 | 2700000000000 | Cycle 78 in shadow | Mike, Jorg & co
13:00 - 17:00 | TCDI setting up & checks IR2 | 4 | 5000000000 | 720 | 3600000000000
17:00 - 19:00 | Set-up & 78 Threading | 2 | 5000000000 | 360 | 1800000000000 | BLM triggers with beam on TDI (should be parasitic). | OP
19:00 - 21:00 | BLM threshold test 78 | 2 | 5000000000 | 360 | 1800000000000
21:00 - 01:00 | Injection aperture IR8 | 4 | 5000000000 | 720 | 3600000000000 |  | ABT
SUN 01:00 - 06:00 | 78 aperture | 5 | 5000000000 | 900 | 4500000000000 |  | Frank Zimmermann & co | Stefano - N | Ron - N
06:00 - 10:00 | higher-order studies of sextupoles, skew sextupole and octupole circuits S78 | 4 | 5000000000 | 720 | 3600000000000 |  | Stefano & co
10:00 - 14:00 | LHCb Spectrometer & compensation | 4 | 5000000000 | 720 | 3600000000000 |  | Mike, Jorg & co
14:00 - 18:00 | Injection protection - TI8/IR8 | 4 | 5000000000 | 720 | 3600000000000 |  | Verena, colls,ABT
18:00 - 02:00 | injection region studies IR78 | 8 | 5000000000 | 1440 | 7200000000000 | aperture, waveform studies, protection | ABT | Verena - A | Alick | Matteo - A | GHH - A
02:00 - 06:00 | Collimator studies | 4 | 5000000000 | 720 | 3600000000000 |  | Coll | Stefano - N | Guy or Ron - N
| TOTAL | 56 |  | 5760 | 48600000000000
| DAYS | 2.3333

## including 67 & 56
|  | Duration | Intensity | # shots | ò Intensity | Comments | Names
|  | h | p+ |  | p+
Friday 14:00 | Close LHC |  |  |  |  | BIS, transfer lines, EIS etc
18:00 - 21:00 | Beam into 78, thread to IR7, check, beam to IR6, check, beam toTCTs IR5. | 3 | 5000000000 | 540 | 2700000000000 | First look - check systems - leave beam dump for the moment - cycle 23 in shadow
21:00 - 22:00 | S23 Injection & beam to 3 | 1 | 5000000000 | 180 | 900000000000 | Same settings at last time - should be straightforward. Alice would like 30' on the TED | OP
22:00 - 24:00 | BLM threshold test 23 | 2 | 5000000000 | 360 | 1800000000000 |  | Bernd
SAT 00:00 - 03:00 | Polarity checks 23 - revisited | 3 | 5000000000 | 540 | 2700000000000 |  | Frank Zimmermann & co
03:00 - 05:00 | Momentum aperture measurements in sector 2-3 | 2 | 5000000000 | 360 | 1800000000000 | (arc + IP) | Stefano & co
05:00 - 07:00 | BLMs/collimators point 3 | 2 | 5000000000 | 360 | 1800000000000 |  | Stefano & co
07:00 - 10:00 | Alice Spectrometer | 3 | 5000000000 | 540 | 2700000000000 | Cycle 78 in shadow | Mike, Jorg & co
10:00 - 12:00 | TDI & TCLI IP2 | 2 | 5000000000 | 360 | 1800000000000 |  | Colls
12:00 -14:00 | ACCESS
14:00 - 15:00 | Thread beam to 5 - delayed | 1 | 5000000000 | 180 | 900000000000
15:00 - 16:00 | Initial beam dump set-up - delayed | 1 | 5000000000 | 180 | 900000000000 |  | ABT
16:00 - 18:00 | Dispersion to 5 - delayed | 1.5 | 5000000000 | 270 | 1350000000000 | TCTs right of 5 | Malika & op
18:00 - 19:00 | Kick response to 5 - delayed | 1.5 | 5000000000 | 270 | 1350000000000 | TCTs right of 5 | Kajetan
19:00 - 24:00 | Dump studies - postponed | 5 | 5000000000 | 900 | 4500000000000 | beam into 6 - dump channel | ABT
24:00 - 05:00 | 56/67/78 aperture | 5 | 5000000000 | 900 | 4500000000000 | TCTs right of 5 | Stefano & co
05:00 - 07:00 | Collimators IR7 | 2 | 5000000000 | 360 | 1800000000000 | beam to 7
07:00 - 09:00 | BLM threshold test 78 | 2 | 5000000000 | 360 | 1800000000000
09:00 - 12:00 | Dump Studies | 3 | 5000000000 | 540 | 2700000000000 | beam to 7 (or 5 if required) | ABT
12:00 - 14:00 | Steering at injection | 2 | 5000000000 | 360 | 1800000000000 | plus TDI scan
14:00 - 16:00 | IR injection region aperture | 2 | 5000000000 | 360 | 1800000000000
16:00 - 18:00 | MKI | 2 | 5000000000 | 360 | 1800000000000
18:00 - 19:00 | Kick response TI8/LHC | 1 | 5000000000 | 180 | 900000000000 |  | Kajetan
19:00 - 24:00 | Injection protection studies | 5 | 5000000000 | 900 | 4500000000000 |  | Verena, colls, ABT
01:00 - 06:00 | Higher order polarity checks | 5 | 5000000000 | 900 | 4500000000000 | 78, 67, 56 as requried | Frank Z & co
|  | 53 |  | 7200 | 45900000000000
| TOTAL | 2.2083 |  |  | 13500000000000 | into S23
| DAYS |  |  |  | 32400000000000 | into S78

## Shifts
|  | EIC |  |  | OPERATOR
| M | A | N | M | A | N
FRIDAY | - | - | Stefano | - | - | Louis
SATURDAY | Walter | Alick | Stefano | Rossano |  | Louis
SUNDAY | Alick | Verena | Stefano | Lasse | GHH | Louis