## Sheet1
Period | Version 10.03.2008: 1Q2008 WLCG Service Coordination Planning for LCG Tier 1 Capacity: Planned pledges, Available and Required by Experiments for Scheduled and Service Challenge Activities
1Q2008 | Tier 1 Capacity: Available vs. Required (Scheduled) | [8 empty] | Scheduled Capacity Required by LHC Experiments and Site Jan. Disk Allocations
WLCG Site | CPU KSi2K |  |  | Disk TB |  |  | Tape TB |  |  | ALICE |  |  |  | ATLAS |  |  |  | CMS |  |  |  | LHCb
| 2007/8 pledge | Installed | Required | 2007/8 pledge | Installed | Required | 2007/8 pledge | Installed | Required | CPU | Disk | Alloc. | Tape | CPU | Disk | Alloc. | Tape | CPU | Disk | Alloc. | Tape | CPU | Disk | Alloc. | Tape
ASGC | 1770 | 3060 | 942.4 | 900 | 1350 | 340.4 | 800 | 800 | 453 |  |  |  |  | 198.4 | 136.4 | 67 | 93 | 744 | 204 | 218 | 360
CC-IN2P3 | 1286 | 2568 | 1500.7 | 729 | 1394 | 753.6 | 745 | 1469 | 705 | 428 | 220 | 275 | 181 | 416 | 286 | 601 | 195 | 620 | 170 | 346 | 300 | 36.7 | 77.6 | 173 | 29
FZK/GridKa | 1860 | 1864 | 2093.1 | 880 | 878 | 824.6 | 1010 | 1007 | 971.1 | 1003 | 323 | 200 | 441 | 320 | 220 | 280 | 150 | 744 | 204 | 330 | 360 | 26.1 | 77.6 | 68 | 20.1
INFN/CNAF | 1300 | 1300 | 1987.1 | 500 | 500 | 874.6 | 650 | 650 | 862.4 | 650 | 305 | 24 | 213 | 320 | 220 | 160 | 150 | 992 | 272 | 177 | 480 | 25.1 | 77.6 | 64 | 19.4
NDGF | 688 | 688 | 766 | 385 | 385 | 370 | 273 | 273 | 634.5 | 622 | 271 |  | 567 | 144 | 99 |  | 67.5
PIC | 501 | 477 | 535 | 218 | 694 | 224.9 | 243 | 293 | 265.1 |  |  |  |  | 144 | 99 | 221 | 67.5 | 372 | 102 | 187 | 180 | 19 | 23.9 | 156 | 17.6
RAL | 1300 | 1825 | 936.1 | 640 | 705 | 492.6 | 1080 | 738 | 454.4 | 30 | 15 | 21 | 13 | 384 | 264 | 270 | 180 | 496 | 136 | 325 | 240 | 26.1 | 77.6 | 110 | 21.4
SARA-NIKHEF | 1677 | 774 | 629.9 | 1059 | 253 | 452.6 | 719 | 52 | 296.9 | 195 | 100 | 3 | 84 | 400 | 275 | 152 | 187.5 |  |  |  |  | 34.9 | 77.6 | 62 | 25.4
TRIUMF | 160 | 905 | 137.6 | 110 | 500 | 94.6 | 80 | 385 | 64.5 |  |  |  |  | 137.6 | 94.6 | 248 | 64.5
US-ATLAS BNL | 2560 | 2400 | 736 | 1100 | 1100 | 506 | 603 | 1320 | 345 |  |  |  |  | 736 | 506 | 520 | 345
US-CMS FNAL | 1792 | 3000 | 2232 | 700 | 1700 | 612 | 300 | 1600 | 1080 | [8 empty] | 2232 | 612 | 700 | 1080
US-ALICE |  | 180 | 338 |  | 45 | 104 |  | 35 | 0 | 338 | 104 |  | 0
TOTALS | 14894 | 19041 | 12833.9 | 7221 | 9504 | 5649.9 | 6503 | 8622 | 6131.9 | 3266 | 1338 | 523 | 1499 | 3200 | 2200 | 2519 | 1500 | 6200 | 1700 | 2283 | 3000 | 167.9 | 411.9 | 633 | 132.9
CERN Tier-0 | 4480 |  |  | 330 |  |  | 1620 |  |  | 53 | 14 |  | 66 | 1900 | 80 |  | 400 | 1900 | 100 |  | 800 | 140 | 110 |  | 250
CERN CAF | 3090 |  |  | 960 |  |  | 790 |  |  | 26 | 3 |  | 0 | 800 | 200 |  | 60 | 1900 | 400 |  | 400 | 0 | 30 |  | 0
CERN Tier-1 | [9 empty] | 900 | 340 |  | 330
CERN Total | 7570 | 11000 | 7619 | 1290 | 2500 | 1277 | 2410 | 5000 | 2306 | 979 | 357 | 286 | 396 | 2700 | 280 | 390 | 460 | 3800 | 500 | 331 | 1200 | 140 | 140 | 179 | 250
Note on A25: renshall: The experiment requirements are for known activities and do not include those for individual or sub-group members of experiments nor for unscheduled activities such as event reprocessing to validate a new software release or urgent generation of special Monte Carlo samples. Typically these add 10 to 20% to the requirement and site experiment team users should be consulted.
Note on I25: renshall: ATLAS, LHCB and ALICE requirements and shares are direct from the experiments. CMS requirements are those of the 2007 TDR addendum spread over sites according to the 2008 site disk resource offers (which add to 100%). The site pledges are those from 1 July 2007 till 31 March 2008. From 1 April 2008 a new round of pledged capacity should be available at the Tier 1 sites. The disk alloc. columns show the allocated disk resources as of the date of the version of the spreadsheet. This table does not yet include any additional resources required for the ccrc'08 February run.