## Sheet1
Period | Version 17.02.2010: 1Q2010 WLCG Service Coordination Planning for LCG Tier 0+1 Capacity: Planned pledges, Available and Approved for Experiments Scheduled and Service Challenge Activities
1Q2010 | Tier 1 Capacity:Pledged, Available and Approved (Scheduled) | [8 empty] | Scheduled Capacity Approved by C-RSG/CRRB and Site December Disk Allocations | [15 empty] | Site percentage shares
WLCG Site | CPU HEP-SPEC06 |  |  | Disk TB |  |  | Tape TB |  |  | ALICE |  |  |  | ATLAS |  |  |  | CMS |  |  |  | LHCb |  |  |  | Site Offers normalised to 100%
| 2009/10 pledge | Installed | Approved | 2009/10 pledge | Installed | Approved | 2009/10 pledge | Installed | Approved | CPU | Disk | Alloc. | Tape | CPU | Disk | Alloc. | Tape | CPU | Disk | Alloc. | Tape | CPU | Disk | Alloc. | Tape | ALICE | ATLAS | CMS | LHCB
ASGC | 20000 | 9728 | 13073 | 3000 | 2500 | 1898.5 | 3000 | 2500 | 2259.5 |  |  |  |  | 5516 | 826 | 765 | 560 | 7557 | 1072.5 | 635 | 1699.5 | [5 empty] | 0.07 | 0.165
CC-IN2P3 | 27066 | 31992 | 23574 | 3070 | 4600 | 2802.6 | 3550 | 5200 | 3907 | 5070 | 481 | 63 | 1651 | 8668 | 1298 | 1753 | 880 | 5496 | 780 | 748 | 1236 | 4340 | 243.6 | 479 | 140 | 0.13 | 0.11 | 0.12 | 0.14
FZK/GridKa | 41420 | 41420 | 31066 | 5142 | 5142 | 3542.2 | 7190 | 7190 | 7069 | 15210 | 1443 | 1329 | 4953 | 7880 | 1180 | 1219 | 800 | 5496 | 780 | 1156 | 1236 | 2480 | 139.2 | 315 | 80 | 0.39 | 0.1 | 0.12 | 0.08
INFN/CNAF | 21200 | 12000 | 15673 | 2300 | 1300 | 1821.3 | 2600 | 1500 | 2917.7 | 4134 | 392.2 | 292 | 1346.2 | 3940 | 590 | 506 | 400 | 4809 | 682.5 | 473 | 1081.5 | 2790 | 156.6 | 166 | 90 | 0.106 | 0.05 | 0.105 | 0.09
NDGF | 12120 | 12120 | 9591 | 1580 | 1580 | 1104.5 | 1660 | 1660 | 2328.5 | 6045 | 573.5 | 204 | 1968.5 | 3546 | 531 | 1213 | 360 | [8 empty] | 0.155 | 0.045
PIC | 10364 | 10364 | 7908 | 1702 | 1979 | 1014 | 1844 | 2060 | 1091 |  |  |  |  | 3152 | 472 | 1063 | 320 | 3206 | 455 | 730 | 721 | 1550 | 87 | 186 | 50 |  | 0.04 | 0.07 | 0.05
RAL | 23100 | 23100 | 24679 | 3401 | 2684 | 2590.5 | 4045 | 2070 | 2537.5 | 975 | 92.5 | 121 | 317.5 | 8274 | 1239 | 1420 | 840 | 4580 | 650 | 760 | 1030 | 10850 | 609 | 321 | 350 | 0.025 | 0.105 | 0.1 | 0.35
SARA-NIKHEF | 30176 | 40432 | 24757 | 3753 | 2757 | 2692.3 | 3548 | 460 | 2598.7 | 3159 | 299.7 | 4 | 1028.7 | 12608 | 1888 | 1553 | 1280 |  |  |  |  | 8990 | 504.6 | 492 | 290 | 0.081 | 0.16 |  | 0.29
TRIUMF | 5680 | 3620 | 3940 | 990 | 500 | 590 | 750 | 385 | 400 |  |  |  |  | 3940 | 590 | 500 | 400 | [9 empty] | 0.05
US-ATLAS BNL | 29348 | 29348 | 21276 | 5822 | 3800 | 3186 | 3277 | 3200 | 2160 |  |  |  |  | 21276 | 3186 | 3500 | 2160 | [9 empty] | 0.27
US-CMS FNAL | 20400 | 20400 | 14656 | 2600 | 2600 | 2080 | 7100 | 7100 | 3296 | [8 empty] | 14656 | 2080 | 2500 | 3296 | [6 empty] | 0.32
US-ALICE |  | 720 | 4407 |  | 45 | 418.1 |  | 35 | 1435.1 | 4407 | 418.1 |  | 1435.1 | [12 empty] | 0.113
TOTALS | 240874 | 235244 | 194600 | 33360 | 29487 | 23740 | 38564 | 33360 | 32000 | 39000 | 3700 | 2013 | 12700 | 78800 | 11800 | 13492 | 8000 | 45800 | 6500 | 7002 | 10300 | 31000 | 1740 | 1959 | 1000 | 1 | 1 | 1 | 1
CERN Tier-0 | 95632 |  | 120000 | 5656 |  | 4920 | 22432 |  | 15500 | 39000 | 3100 |  | 3000 | 28900 | 700 |  | 5100 | 37100 | 400 |  | 6400 | 15000 | 720 |  | 1000
CERN CAF | 36248 |  | 35600 | 4409 |  | 3900 | 2651 |  | 1000 |  | 0 |  | 0 | 28000 | 2600 |  | 0 | 7600 | 1300 |  | 1000 | 0 | 0 |  | 0
CERN Tier-1 | [10 empty] | 0 |  | 0
CERN Total | 131880 | 157604 | 155600 | 10065 | 7731 | 8820 | 25083 | 25083 | 16500 | 39000 | 3100 | 1713 | 3000 | 56900 | 3300 | 2892 | 5100 | 44700 | 1700 | 2405 | 7400 | 15000 | 720 | 721 | 1000
Note on A23: renshall: Site pledges and approved experiment requirements for 1Q2010 are here those as agreed by the Autumn 2009 crrb. The site approved shares per experiment are values offered by the sites then normalised to sum to 100% o the approved Tier 1 totals and dating from 2009. The US-ALICE share is 7% normalised to 11% but not offically confirmed and the installed values are very out of date. In this table the cpu values are in the HS06 unit (a factor of 4 more than the KSi2K unit).