## Sheet1
Period | Version 07.05.2007: 2Q2007 WLCG Service Coordination Planning for LCG Tier 1 Capacity: Planned pledges, Available and Required by Experiments for Scheduled and Service Challenge Activities
2Q2007 | Tier 1 Capacity: Available vs. Required (Scheduled) | [8 empty] | Scheduled Capacity Required by LHC Experiments and Site Disk Allocations
WLCG Site | CPU KSi2K |  |  | Disk TB |  |  | Tape TB |  |  | ALICE |  |  |  | ATLAS |  |  |  | CMS |  |  |  | LHCb
| 2006/7 pledge | Installed | Required | 2006/7 pledge | Installed | Required | 2006/7 pledge | Installed | Required | CPU | Disk | Alloc. | Tape | CPU | Disk | Alloc. | Tape | CPU | Disk | Alloc. | Tape * | CPU | Disk | Alloc. | Tape
ASGC | 950 | 945 | 447 | 400 | 474 | 97 | 500 | 304 | 157 |  |  |  |  | 267 | 27 | 67 | 41 | 180 | 70 | 218 | 116
CC-IN2P3 | 1170 | 1171 | 1448 | 520 | 356 | 354 | 535 | 510 | 370 | 321 | 165 | 20 | 136 | 467 | 52 | 149 | 91 | 180 | 70 | 100 | 116 | 480 | 67 | 87 | 27
FZK/GridKa | 1030 | 1864 | 1562 | 280 | 284 | 430 | 393 | 1007 | 544 | 752 | 242 | 61 | 331 | 364 | 51 | 71 | 89 | 180 | 70 | 116 | 106 | 266 | 67 | 51 | 18
INFN/CNAF | 1800 | 1500 | 1416 | 850 | 450 | 489 | 850 | 500 | 447 | 488 | 229 | 22 | 160 | 260 | 33 | 74 | 51 | 420 | 160 | 110 | 218 | 248 | 67 | 51 | 18
NDGF | 520 | 683 | 657 | 160 | 189 | 227 | 240 | 186 | 453 | 467 | 203 |  | 425 | 190 | 24 |  | 28
PIC | 250 | 450 | 495 | 140 | 88 | 166 | 158 | 161 | 150 |  |  |  |  | 190 | 29 | 26 | 42 | 180 | 70 | 26 | 92 | 125 | 67 | 36 | 16
RAL | 980 | 810 | 729 | 450 | 318 | 188 | 664 | 384 | 185 | 23 | 11 | 21 | 10 | 260 | 40 | 114 | 71 | 180 | 70 | 120 | 84 | 266 | 67 | 64 | 20
SARA-NIKHEF | 306 | 774 | 1039 | 170 | 148 | 187 | 143 | 52 | 171 | 146 | 75 | 3 | 63 | 450 | 45 | 41 | 85 |  |  |  |  | 443 | 67 | 39 | 23
TRIUMF | 150 | 305 | 183 | 12 | 24 | 27 | 12 | 12 | 35 |  |  |  |  | 183 | 27 | 23 | 35
US-ATLAS BNL | 1120 | 1120 | 831 | 520 | 520 | 79 | 300 | 600 | 165 |  |  |  |  | 831 | 79 | 520 | 165
US-CMS FNAL | 728 | 2250 | 720 | 100 | 720 | 280 | 250 | 500 | 406 | [8 empty] | 720 | 280 | 700 | 406
US-ALICE |  | 180 | 254 |  | 45 | 78 |  | 35 | 0 | 254 | 78 |  | 0
TOTALS | 9004 | 12052 | 9781 | 3602 | 3616 | 2602 | 4045 | 4251 | 3083 | 2451 | 1003 | 127 | 1125 | 3462 | 407 | 1085 | 698 | 2040 | 790 | 1390 | 1138 | 1828 | 402 | 328 | 122
CERN Tier-0 | 2400 |  |  | 230 |  |  | 1500 |  |  | 53 | 14 |  | 66 | 1900 | 80 |  | 400 | 1900 | 100 |  | 800
CERN CAF | 1000 |  |  | 540 |  |  | 0 |  |  | 26 | 3 |  | 0 | 800 | 200 |  | 60 | 1900 | 400 |  | 400
CERN Total | 3400 | 3174 | 7022 | 770 | 1290 | 864 | 1500 | 3000 | 1791 | 79 | 17 | 286 | 66 | 2700 | 280 | 390 | 460 | 3800 | 500 | 331 | 1200 | 443 | 67 | 179 | 65
Note on A24: renshall: The experiment requirements are for known activities and do not include those for individual or sub-group members of experiments nor for unscheduled activities such as event reprocessing to validate a new software release or urgent generation of special Monte Carlo samples. Typically these add 10 to 20% to the requirement and site experiment team users should be consulted.
Note on I24: renshall: Changes to this table from the version of 7.02.2007 are: new values from ALICE (Y.Schutz, 9 Feb.) with reduced tape requirements; addition of LHCb requirements for June and July and all now changed to gross values; replacement of site 'Available' values by 'Installed' values being those from the end of January accounting plus already announced increases for 2Q2007; addition of new columns of Allocated disk space (in italics) per site per experiment taken from the end of Febrary accounting; change pledges from 2007 values, which need to be available to experiments from 1 July 2007 till 1 April 2008, to 2006/7 values which should be available up till 30 June 2007; add CERN resources, using full 2007 requests, for completeness. 10 April: Change PIC installed disk from 200 TB to current value of 70 TB. 17 April: FZK revised cpu and tape pledges for 2007/8 already available from the start of 2Q2007. 26 April: SARA-NIKHEF report increased total disk space and allocations for ATLAS and LHCB. 30 April: Update site experiment disk allocations from the March accounting returns. 7 May: Updates received from IN2P3, PIC and RAL.