## Sheet1
Period | Version 24.06.2008: 2Q2008 WLCG Service Coordination Planning for LCG Tier 1 Capacity: Planned pledges, Available and Required by Experiments for Scheduled and Service Challenge Activities
2Q2008 | Tier 1 Capacity: Available vs. Required (Scheduled) | [8 empty] | Scheduled Capacity Required by LHC Experiments and Site May Disk Allocations
WLCG Site | CPU KSi2K |  |  | Disk TB |  |  | Tape TB |  |  | ALICE |  |  |  | ATLAS |  |  |  | CMS |  |  |  | LHCb
| 2008/9 pledge | Installed | Required | 2008/9 pledge | Installed | Required | 2008/9 pledge | Installed | Required | CPU | Disk | Alloc. | Tape | CPU | Disk | Alloc. | Tape | CPU | Disk | Alloc. | Tape | CPU | Disk | Alloc. | Tape
ASGC | 3400 | 3400 | 2467 | 1500 | 1500 | 1673 | 1300 | 1300 | 1872 |  |  |  |  | 1123 | 665 | 451 | 500 | 1344 | 1008 | 404 | 1372
CC-IN2P3 | 4240 | 4240 | 4882 | 2375 | 1394 | 2747 | 2470 | 2470 | 2863 | 1414 | 560 | 55 | 812 | 2356 | 1395 | 575 | 1049 | 864 | 648 | 521 | 882 | 248 | 144 | 127 | 120
FZK/GridKa | 5672 | 4522 | 7045 | 2933 | 2293 | 3579 | 3629 | 2449 | 4314 | 3939 | 1560 | 300 | 2262 | 1812 | 1073 | 825 | 807 | 1152 | 864 | 499 | 1176 | 142 | 82 | 195 | 69
INFN/CNAF | 3000 | 3000 | 3994 | 1300 | 1300 | 2289 | 1500 | 1500 | 2453 | 1111 | 440 | 28 | 638 | 1812 | 1073 | 198 | 807 | 912 | 684 | 190 | 931 | 159 | 92 | 64 | 77
NDGF | 2172 | 2650 | 2633 | 1079 | 870 | 1203 | 930 | 320 | 1407 | 1818 | 720 | 74 | 1044 | 815 | 483 | 385 | 363
PIC | 1509 | 1105 | 1432 | 967 | 707 | 930 | 953 | 520 | 945 |  |  |  |  | 815 | 483 | 287 | 363 | 528 | 396 | 176 | 539 | 89 | 51 | 149 | 43
RAL | 3139 | 3139 | 3714 | 1920 | 1920 | 2283 | 1900 | 2070 | 2140 | 152 | 60 | 4 | 87 | 2174 | 1288 | 455 | 968 | 768 | 576 | 314 | 784 | 620 | 359 | 145 | 301
SARA-NIKHEF | 4382 | 774 | 3334 | 2510 | 373 | 1858 | 1813 | 200 | 1577 | 556 | 220 | 4 | 319 | 2265 | 1341 | 150 | 1009 |  |  |  |  | 513 | 297 | 78 | 249
TRIUMF | 905 | 905 | 779 | 500 | 500 | 461 | 385 | 385 | 347 |  |  |  |  | 779 | 461 | 500 | 347
US-ATLAS BNL | 4844 | 4844 | 4167 | 3136 | 2100 | 2468 | 1715 | 1800 | 1856 |  |  |  |  | 4167 | 2468 | 1345 | 1856
US-CMS FNAL | 4300 | 4500 | 3840 | 2000 | 1700 | 2880 | 4700 | 4100 | 3920 | [8 empty] | 3840 | 2880 | 1500 | 3920
US-ALICE |  | 180 | 1111 |  | 45 | 440 |  | 35 | 638 | 1111 | 440 |  | 638
TOTALS | 37563 | 33259 | 39398 | 20220 | 14702 | 22811 | 21295 | 17149 | 24332 | 10101 | 4000 | 465 | 5800 | 18118 | 10730 | 5171 | 8069 | 9408 | 7056 | 3604 | 9604 | 1771 | 1025 | 758 | 859
CERN Tier-0 | 11170 |  | 11165 | 2423 |  | 2422 | 10780 |  | 10779 | 1800 | 1600 |  | 3300 | 3705 | 152 |  | 2449 | 5300 | 400 |  | 4400 | 360 | 270 |  | 630
CERN CAF | 4680 |  | 4681 | 3126 |  | 3126 | 1270 |  | 1270 | 500 | 100 |  | 0 | 2081 | 1146 |  | 370 | 2100 | 1800 |  | 900 | 0 | 80 |  | 0
CERN Tier-1 | [9 empty] | 0 | 0 |  | 0
CERN Total | 15850 | 15850 | 15846 | 5549 | 5549 | 5548 | 12050 | 12050 | 12049 | 2300 | 1700 | 286 | 3300 | 5786 | 1298 | 390 | 2819 | 7400 | 2200 | 331 | 5300 | 360 | 350 | 179 | 630
Note on A25: renshall: The experiment requirements are for known activities and do not include those for individual or sub-group members of experiments nor for unscheduled activities such as event reprocessing to validate a new software release or urgent generation of special Monte Carlo samples. Typically these add 10 to 20% to the requirement and site experiment team users should be consulted.
Note on I25: renshall: ATLAS, LHCB and ALICE shares are direct from the experiments normalised to 100% over their Tier 1 sites. CMS shares are the site 2008 average cpu+disk resource offers to cms normalised to 100%. From 1 April 2008 this new round of pledged capacity should be available to be used by the experiments at the Tier 1 sites. The disk alloc. columns show the allocated disk resources as of the date of the version of the spreadsheet. The installed resources are the advance capacity planning for 1 April from all the Tier 1 sites. This table does not yet include any additional resources required for the ccrc'08 May run.