## Sheet1
Period | Version 07.11.2007: 4Q2007 WLCG Service Coordination Planning for LCG Tier 1 Capacity: Planned pledges, Available and Required by Experiments for Scheduled and Service Challenge Activities
4Q2007 | Tier 1 Capacity: Available vs. Required (Scheduled) | [8 empty] | Scheduled Capacity Required by LHC Experiments and Site Sep. Disk Allocations
WLCG Site | CPU KSi2K |  |  | Disk TB |  |  | Tape TB |  |  | ALICE |  |  |  | ATLAS |  |  |  | CMS |  |  |  | LHCb
| 2007/8 pledge | Installed | Required | 2007/8 pledge | Installed | Required | 2007/8 pledge | Installed | Required | CPU | Disk | Alloc. | Tape | CPU | Disk | Alloc. | Tape | CPU | Disk | Alloc. | Tape | CPU | Disk | Alloc. | Tape
ASGC | 1770 | 1770 | 942.4 | 900 | 432 | 340.4 | 800 | 800 | 453 |  |  |  |  | 198.4 | 136.4 | 67 | 93 | 744 | 204 | 218 | 360
CC-IN2P3 | 1286 | 2568 | 1500.7 | 729 | 1394 | 753.6 | 745 | 1469 | 705 | 428 | 220 | 275 | 181 | 416 | 286 | 601 | 195 | 620 | 170 | 346 | 300 | 36.7 | 77.6 | 173 | 29
FZK/GridKa | 1860 | 1864 | 2093.1 | 880 | 878 | 824.6 | 1010 | 1007 | 971.1 | 1003 | 323 | 200 | 441 | 320 | 220 | 280 | 150 | 744 | 204 | 330 | 360 | 26.1 | 77.6 | 68 | 20.1
INFN/CNAF | 1300 | 1300 | 1987.1 | 500 | 500 | 874.6 | 650 | 650 | 862.4 | 650 | 305 | 22 | 213 | 320 | 220 | 74 | 150 | 992 | 272 | 110 | 480 | 25.1 | 77.6 | 51 | 19.4
NDGF | 688 | 688 | 766 | 385 | 240 | 370 | 273 | 112 | 634.5 | 622 | 271 |  | 567 | 144 | 99 |  | 67.5
PIC | 501 | 477 | 535 | 218 | 284 | 224.9 | 243 | 161 | 265.1 |  |  |  |  | 144 | 99 | 114 | 67.5 | 372 | 102 | 133 | 180 | 19 | 23.9 | 36 | 17.6
RAL | 1300 | 820 | 936.1 | 640 | 330 | 492.6 | 1080 | 390 | 454.4 | 30 | 15 | 21 | 13 | 384 | 264 | 114 | 180 | 496 | 136 | 120 | 240 | 26.1 | 77.6 | 64 | 21.4
SARA-NIKHEF | 1677 | 774 | 629.9 | 1059 | 253 | 452.6 | 719 | 52 | 296.9 | 195 | 100 | 3 | 84 | 400 | 275 | 41 | 187.5 |  |  |  |  | 34.9 | 77.6 | 39 | 25.4
TRIUMF | 160 | 905 | 137.6 | 110 | 24 | 94.6 | 80 | 385 | 64.5 |  |  |  |  | 137.6 | 94.6 | 23 | 64.5
US-ATLAS BNL | 2560 | 2600 | 736 | 1100 | 1100 | 506 | 603 | 1000 | 345 |  |  |  |  | 736 | 506 | 520 | 345
US-CMS FNAL | 1792 | 2250 | 2232 | 700 | 720 | 612 | 300 | 500 | 1080 | [8 empty] | 2232 | 612 | 700 | 1080
US-ALICE |  | 180 | 338 |  | 45 | 104 |  | 35 | 0 | 338 | 104 |  | 0
TOTALS | 14894 | 16196 | 12833.9 | 7221 | 6200 | 5649.9 | 6503 | 6561 | 6131.9 | 3266 | 1338 | 521 | 1499 | 3200 | 2200 | 1834 | 1500 | 6200 | 1700 | 1957 | 3000 | 167.9 | 411.9 | 431 | 132.9
CERN Tier-0 | 4480 |  |  | 330 |  |  | 1620 |  |  | 53 | 14 |  | 66 | 1900 | 80 |  | 400 | 1900 | 100 |  | 800 | 140 | 110 |  | 250
CERN CAF | 3090 |  |  | 960 |  |  | 790 |  |  | 26 | 3 |  | 0 | 800 | 200 |  | 60 | 1900 | 400 |  | 400 | 0 | 30 |  | 0
CERN Tier-1 | [9 empty] | 900 | 340 |  | 330
CERN Total | 7570 | 7100 | 7619 | 1290 | 1290 | 1277 | 2410 | 3000 | 2306 | 979 | 357 | 286 | 396 | 2700 | 280 | 390 | 460 | 3800 | 500 | 331 | 1200 | 140 | 140 | 179 | 250
Note on A25: renshall: The experiment requirements are for known activities and do not include those for individual or sub-group members of experiments nor for unscheduled activities such as event reprocessing to validate a new software release or urgent generation of special Monte Carlo samples. Typically these add 10 to 20% to the requirement and site experiment team users should be consulted.
Note on I25: renshall: ATLAS, LHCB and ALICE requirements and shares are direct from the experiments. ALICE requirements increase by 33% from 3Q2007 quarter. CMS requirements are those of the 2007 TDR addendum spread over sites according to the 2008 site disk resource offers (which add to 100%).